## Roles and responsibility
Column 1 | Column 2
Name | Role
Abhishek baral | HomeStay

## Homepage
Column 1 | Column 2
Project name | HomeStay
Clint | Masai
Reference document | FRS
Created by | Abhisek Baral
Creation date | 2024-11-18
Approval date | 2024-12-19
Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13
Test Scenario ID | Test Scenario | Test Case ID | Test Case Description | Steps | Pre conditions | Test Data | Expected Result | Actual Result | Status | Exectuted By | Executed Date | Comments
TS_001 | Validate the working of Sign Up functionality | TC_001 | To verify the presence of the Name field | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name | Open browser Enter url HomeStay Perform task | Abhisek | Text field should be enter | The Name field should be displayed on the Sign-Up page | Pass | Abhisek Baral | 2024-11-19 | Name display
TS_001 | Validate the working of Sign Up functionality | TC_002 | To verify the presence of the Number field | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name 5) Enter Phone Number | Open browser Enter url HomeStay Perform task | 854697.... | Number field should be enter | The Number field should be displayed on the Sign-Up page | Pass | Abhisek Baral | 2024-11-19 | Number display
TS_001 | Validate the working of Sign Up functionality | TC_003 | To verify the absence of the name field and presence of number field click on submit | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Blank 5) Enter Phone Number | Open browser Enter url HomeStay Perform task | NA 854697.... | An error message ("Name is required") should be displayed. | The Name is required should be displayed on the Sign-Up page | Fail | Abhisek Baral | 2024-11-19 | NA
TS_001 | Validate the working of Sign Up functionality | TC_004 | To verify the absence of the number field and presence of name field click on submit | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name in text field 5) Blank | Open browser Enter url HomeStay Perform task | Abhisek NA | An error message ("Phone No. is required") should be displayed. | The Phone No is required should be displayed on the Sign-Up page | Fail | Abhisek Baral | 2024-11-19 | NA
TS_001 | Validate the working of Sign Up functionality | TC_005 | To verify the name with Special characters | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name in text field 5) Enter Phone Number | Open browser Enter url HomeStay Perform task | Ahisek@tg. 854697.... | An error message ("Special characters are not allowed") should be displayed. | The Name shouldn't have Special characters displayed on the Sign-Up page | Fail | Abhisek Baral | 2024-11-19 | NA
TS_001 | Validate the working of Sign Up functionality | TC_006 | To verify the phone no is invalid | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name in text field 5) Enter Phone Number | Open browser Enter url HomeStay Perform task | Ahisek 85469 | An error message ("Invalid Phone Number") should be displayed. | The phone No length is 10 digit | Fail | Abhisek Baral | 2024-11-19 | Len no - 10
TS_001 | Validate the working of Sign Up functionality | TC_007 | To verify special characters in Phone Number | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name in text field 5) Enter Phone Number | Open browser Enter url HomeStay Perform task | Ahisek 8546*97... | An error message ("Special characters are not allowed") should be displayed. | The phone no should have valid digit's | Fail | Abhisek Baral | 2024-11-19 | NA
TS_001 | Validate the working of Sign Up functionality | TC_008 | To verify with the valid credential | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name in text field 5) Enter Phone Number 6) Click on submit | Open browser Enter url HomeStay Perform task | Ahisek 8546978641 | It should be successfully click on submit | OTP sent successfully | Pass | Abhisek Baral | 2024-11-19 | OTP Sent
TS_001 | Validate the working of Sign Up functionality | TC_009 | To verify with the valid credential | 1) Open the browser 2) Click on the URL 3) Click on Sign up 4) Enter Name in text field 5) Enter Phone Number 6) Click on submit 7) Enter valid otp | Open browser Enter url HomeStay Perform task | Ahisek 8546978641 457644 | It should be successfully created account on Home stay. | The sign up successfully completed | Pass | Abhisek Baral | 2024-11-19 | Account Created
TS_002 | Validate the working of Login Functionality | TC_010 | To verify the enter register phone no & OTP | 1) Open the browser 2) Click on the URL 3) Click on Login 4) Enter phone no 5) Enter Sent Otp 6) Click on Login | Open browser Enter url HomeStay Perform task | 8546978641 468666 | User should be Login successfully | The user is successfully login to Web app | Pass | Abhisek Baral | 2024-11-19 | Login Success
TS_002 | Validate the working of Login Functionality | TC_011 | To verify the enter register phone no & invalid OTP | 1) Open the browser 2) Click on the URL 3) Click on Login 4) Enter phone no 5) Enter Sent invalid Otp 6) Click on login | Open browser Enter url HomeStay Perform task | 8546978641 000000 | An error message ("Enter Valid OTP") should be displayed. | The OTP is not correct should be displayed on the Login page | Fail | Abhisek Baral | 2024-11-19 | Login Deny
TS_003 | Validate the stay available & booking for guest | TC_012 | To verify the guest see the details for home stay | 1) Open the browser 2) Click on the URL 3) After Login 4) See on dashbord | Open browser Enter url HomeStay Perform task | NA | The Guest should be see the details of home for stay | User successfully see the detail's of the home stay | Pass | Abhisek Baral | 2024-11-19 | NA
TS_003 | Validate the stay available & booking for guest | TC_013 | To verify the guest can book the house for stay | 1) Open the browser 2) Click on the URL 3) After Login 4) See on dashbord 5) Select house 6) Click on book | Open browser Enter url HomeStay Perform task | NA | The Guest should be book home for stay | User should be successfully booked the house | Pass | Abhisek Baral | 2024-11-19 | Booked house
TS_003 | Validate the stay available & booking for guest | TC_014 | To verify the guest can get notification of booking house | 1) Open the browser 2) Click on the URL 3) After Login 4) See on dashbord 5) Select house 6) Click on book | Open browser Enter url HomeStay Perform task | NA | The Guest should be gating notification for booked house | User gating notification for successfully booked the house | Pass | Abhisek Baral | 2024-11-19 | Get Notified
TS_004 | Validate the bookings and cancel or modify functionality | TC_015 | To verify the guest can see the details of booking house | 1) Open the browser 2) Click on the URL 3) After Login 4) See on dashbord 5) Click on Booking detail | Open browser Enter url HomeStay Perform task | NA | The guest should see all the booking's detail | User should be view the detail of booking | Pass | Abhisek Baral | 2024-11-19 | View Booking
TS_004 | Validate the bookings and cancel or modify functionality | TC_016 | To verify the guest can modify date of booking house | 1) Open the browser 2) Click on the URL 3) After Login 4) See on dashbord 5) Click on Booking detail 6) Modify the date of booking | Open browser Enter url HomeStay Perform task | NA | The guest should be modify the date for booking | The detail should be modified | Pass | Abhisek Baral | 2024-11-19 | Modify the date
TS_004 | Validate the bookings and cancel or modify functionality | TC_017 | To verify the guest can cancel the booking. | 1) Open the browser 2) Click on the URL 3) After Login 4) See on dashbord 5) Click on Booking detail 6) Cancel the booking | Open browser Enter url HomeStay Perform task | NA | The guest should be cancel the booking | The booking should be cancel | Pass | Abhisek Baral | 2024-11-19 | Cancel booking
TS_005 | Validate the all the bookings and contact of the guest detail's | TC_018 | To verify the caretaker can see all the detail's of the guest | 1) Open the browser 2) Click on the URL 3) After Login 4) Caretaker on dashbord 5) Booking detail's | Open browser Enter url HomeStay Perform task | NA | The caretaker should be view the all detail's of the guest | The caretaker can see the detail's | Pass | Abhisek Baral | 2024-11-19 | View Booking
TS_005 | Validate the all the bookings and contact of the guest detail's | TC_019 | To verify the caretaker can see all the booking of the day | 1) Open the browser 2) Click on the URL 3) After Login 4) Caretaker on dashbord 5) Booking detail's | Open browser Enter url HomeStay Perform task | NA | The caretaker should be view the all booking list of the day | The caretaker can see all the booking detail | Pass | Abhisek Baral | 2024-11-19 | View Booking
TS_005 | Validate the all the bookings and contact of the guest detail's | TC_020 | To verify the caretaker can cross verify by the contact of guest | 1) Open the browser 2) Click on the URL 3) After Login 4) Caretaker on dashbord 5) Booking detail's 6) See guest detail's | Open browser Enter url HomeStay Perform task | NA | The caretaker should be call to the guest and conform the booking | The caretaker should be book the house accordingly | Pass | Abhisek Baral | 2024-11-19 | Call Verify
TS_006 | Validate the update & identity proof and payment details on the booking | TC_021 | To verify the caretaker can Update the identity prof of the guest | 1) Open the browser 2) Click on the URL 3) After Login 4) Caretaker on dashbord 5) Booking detail's 6) See guest detail's 7) Update by identity | Open browser Enter url HomeStay Perform task | NA | The caretaker should be upload the identity of the guest | It should Identity successfully updated | Pass | Abhisek Baral | 2024-11-19 | Identity prof
TS_006 | Validate the update & identity proof and payment details on the booking | TC_022 | To verify the caretaker can validate the payment proccess of the guest | 1) Open the browser 2) Click on the URL 3) After Login 4) Caretaker on dashbord 5) Booking detail's 6) See the payment process | Open browser Enter url HomeStay Perform task | NA | The caretaker should be able to see the payment is done or not | It should be payment successfull | Pass | Abhisek Baral | 2024-11-19 | Payment Process
TS_006 | Validate the update & identity proof and payment details on the booking | TC_023 | To verify the caretaker can check the payment proccess of the guest | 1) Open the browser 2) Click on the URL 3) After Login 4) Caretaker on dashbord 5) Booking detail's 6) See the payment process | Open browser Enter url HomeStay Perform task | NA | The caretaker should be able to see the payment is done. | it should be conform booking successfully | Pass | Abhisek Baral | 2024-11-19 | Booked success
TS_007 | Validate the Owner View bookings for the homestay | TC_024 | To verify the owner can see the all booking detail | 1) Open the browser 2) Click on the URL 3) After Login Owner 4) Owner on dashbord 5) Booking detail's | Open browser Enter url HomeStay Perform task | NA | The Owner should be view the all booking list of the day | The Owner should be visible all the booking detail | Pass | Abhisek Baral | 2024-11-19 | View Booking
TS_007 | Validate the Owner View bookings for the homestay | TC_025 | To verify the owner can see the all indivisual & guest booking identity prof | 1) Open the browser 2) Click on the URL 3) After Login Owner 4) Owner on dashbord 5) Booking detail's | Open browser Enter url HomeStay Perform task | NA | The Owner should be view the indivisual & guest booking identity | The owner download successfully the identity of guest and indivisual's | Pass | Abhisek Baral | 2024-11-19 | Identity prof
TS_007 | Validate the Owner View bookings for the homestay | TC_026 | To verify the owner can see the all indivisual & guest booking information | 1) Open the browser 2) Click on the URL 3) After Login Owner 4) Owner on dashbord 5) Booking detail's | Open browser Enter url HomeStay Perform task | NA | The added information should be correct with identity. | The information matched successfully | Pass | Abhisek Baral | 2024-11-19 | Match with prof

## Scenario
Column 1 | Column 2
Project name | TutorialsNinja
Clint | TutorialsNinja
Reference document | FRS
Created by | Karan Soni
Creation date
Approval date
Column 1 | Column 2 | Column 3 | Column 4
S.No | Test Scenario ID | Description | Status
1 | TS_001 | Validate the working of Sign Up functionality | Done
2 | TS_002 | Validate the working of Login Functionality | Done
3 | TS_003 | Validate the stay available & booking for guest | Done
4 | TS_004 | Validate the bookings and cancel or modify functionality | Done
5 | TS_005 | Validate the all the bookings and contact of the guest detail's | Done
6 | TS_006 | Validate the update & identity proof and payment details on the booking | Done
7 | TS_007 | Validate the Owner View bookings for the homestay | Done

## Sheet1
test plan | Done
mind map | Done
test case and test scenarios | Done
defect report
summary
test execution | Done